## Dashboard
PROJECT REPORTING DASHBOARD
DATE | TOTAL ITERATION | 2 | SPRINT 1 START DATE | ITERATION DURATION | 1.5 days | SPRINT 2 START DATE | Team Size
Note:- To view the Burndown chart for a particular day the next day should be selected in the Sprint Progress dropdown. For viewing the complete Sprint Burndown chart the status should be set to completed in the dropdown

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | User Story Point | Assignee | Status
2 | 1 | US-01 | As a visitor, I should be able to login to the application by providing my credentials i.e. – contact number and password, so that I can avail all the services of the application. | MUST HAVE | 1 | 1084752 | 1- Not Started
1 | 1 | US-02 | As a visitor, I should be able to “Register” with the application, by providing details like name, email id, contact number and password, so that, I can use the services and get the benefits of a registered user. | MUST HAVE | 1 | 1084752 | 1- Not Started
1 | 1 | US-03 | As a visitor or a registered user, I should be able to see Hot deals that are available and search for other available packages, so that I can explore all the packages available for booking. | MUST HAVE | 1 | 1084752 | 1- Not Started
1 | 2 | US-04 | As a visitor or a registered user, I should be able to view package details, so that I can review the whole package. | MUST HAVE | 2 | 1084752 | 1- Not Started
2 | 2 | US-05 | As a logged-in user, I should be able to Book a desired package. | MUST HAVE | 2 | 1084752 | 1- Not Started
2 | 2 | US-06 | As a logged-in user, I should be able to view my planned trips. | MUST HAVE | 2 | 1084752 | 1- Not Started
2 | 2 | US-07 | As a logged-in user, I should be able cancel a particular booking. | MUST HAVE | 2 | 1084752 | 1- Not Started
2 | 2 | US-08 | As a logged-in user, I should be able to logout. | MUST HAVE | 2 | 1084752 | 1- Not Started
Note on F1: Kindly refrain from providing more than 8 points to user stories
Note on F2: Kindly refrain from providing more than 8 points to user stories

## Sprint I Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3
[8 empty] | 19.5 | 9 | 7 | 0
SPRINT 1 BACKLOG
US-01 | T1 | Validate input contact no & passward. | 2020-05-08 | 2020-05-08 | 1084752 | Coding | 3- Completed | 1 | 1 | 0
| T2 | Varify contact no and password from database. | 2020-05-08 | 2020-05-08 | 1084752 | Coding | 3- Completed | 1 | 1 | 0
| T3 | After successfully logging navigate home page | 2020-05-08 | 2020-05-08 | 1084752 | Coding | 3- Completed | 1.5 | 1 | 0
| T4 | In case of logging failed displaying appropriate message | 2020-05-08 | 2020-05-08 | 1084752 | Coding | 3- Completed | 1 | 1 | 0
| T5 | Unit testing | 2020-05-08 | 2020-05-08 | 1084752 | Unit Test | 3- Completed | 1 | 1 | 0
| T1 | Validate inputs name,emailid,contact no. & password for registration. | 2020-05-08 | 2020-05-08 | 1084752 | Coding | 3- Completed | 2 | 2 | 0
US-02 | T2 | Check the contact no if it is already available in database | 2020-05-08 | 2020-05-08 | 1084752 | Coding | 3- Completed | 2 | 1 | 0
| T3 | After successfully registeration displaying success message. | 2020-05-08 | 2020-05-08 | 1084752 | Coding | 3- Completed | 1 | 1 | 0
| T4 | In case of error displaying appropriate message. | 2020-05-11 | 2020-05-11 | 1084752 | Coding | 3- Completed | 1 | 0 | 1
| T1 | Adding all hot deals to database and make them able to view in home page. | 2020-05-11 | 2020-05-11 | 1084752 | Coding | 3- Completed | 2 | 0 | 2
US-03 | T2 | Make all hotdeals package able to view in navbar link Hotdeals | 2020-05-11 | 2020-05-11 | 1084752 | Coding | 3- Completed | 2 | 0 | 1
| T3 | View particular package in search. | 2020-05-11 | 2020-05-11 | 1084752 | Coding | 3- Completed | 2 | 0 | 2
| T4 | In case of error displaying appropriate message. | 2020-05-11 | 2020-05-11 | 1084752 | Coding | 3- Completed | 2 | 0 | 1
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 2 work

## Sprint II Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3
[8 empty] | 17 | 8.5 | 5.5 | 0
SPRINT 2 BACKLOG
US-04 | T1 | create a side bar having 3 tabs overview,itinerary,book | 2020-05-12 | 2020-05-12 | 1084752 | Coding | 3- Completed | 2 | 2 | 0
| T2 | Create Booking form | 2020-05-12 | 2020-05-12 | 1084752 | Coding | 3- Completed | 1.5 | 1 | 0
| T3 | Validate the booking form | 2020-05-12 | 2020-05-12 | 1084752 | Coding | 3- Completed | 1 | 1 | 0
| T4 | Redirect to login page before booking if not logged in. | 2020-05-12 | 2020-05-12 | 1084752 | Coding | 3- Completed | 0.5 | 0.5 | 0
| T5 | Unit Testing | 2020-05-12 |  |  | Unit Test | 1- Not Started
T6
T7
T8
US-05 | T1 | Validate User Login and Create a booking from package detail card | 2020-05-12 | 2020-05-12 | 1084752 | Coding | 3- Completed | 2 | 2
| T2 | Validate Booking Criteria | 2020-05-12 | 2020-05-12 | 1084752 | Coding | 3- Completed | 2 | 1
| T3 | Update the Database | 2020-05-12 | 2020-05-12 | 1084752 | Coding | 3- Completed | 1 | 1
| T4 | Unit testing | 2020-05-12 |  | 1084752 | Coding | 1- Not Started
T5
T6
T7
US-06 | T1 | Display the Booked Package booked by the logged in Users | 2020-05-13 | 2020-05-13 | 1084752 | Coding | 3- Completed | 2 | 0 | 1.5
| T2 | Unit testing | 2020-05-13 |  | 1084752 | Unit Test | 1- Not Started
T3
T4
T5
T6
T7
US-07 | T1 | Provide cancel booking option to the logged in user. | 2020-05-13 | 2020-05-13 | 1084752 | Coding | 3- Completed | 2 | 0 | 2
| T2 | Update the Database | 2020-05-13 | 2020-05-13 | 1084752 | Coding | 3- Completed | 2 | 0 | 1
| T3 | Unit testing | 2020-05-13 |  | 1084752 | Unit Test | 1- Not Started
T4
T5
T6
T7
US-08 | T1 | creating logout function | 2020-05-13 | 2020-05-13 | 1084752 | Coding | 3- Completed | 1 | 0 | 1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
T1
T2
T3
T4
T5
T6
T7
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 2 work

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2020-05-08 | 2020-05-11 | Rakesh Karhana | Learning prime react and give equal importance to user stories. | Stop wasting time on a particular user story if you are stuck. | Enhancing UI and maintaining agile sheet | complete user stories one by one learn prime react.
2 | 2 | 2020-05-08 | 2020-05-11 | Rakesh Karhana | unit testing | create component and maintain agile | Create component and maintain agile sheet. | Focus on completion of sprint 2

## Reference Data
SPRINT I BURN-DOWN CHART DATA
Sprint | Day | Planned | Actual | TEAM VELOCITY CHART
1 |  | 19.5 | 16
| 1 | 13 | 9 | Sprint | Planned | Actual
| 2 | 6.5 | 7 | 1 | 19.5 | 16
|  |  |  | 2 | 17 | 14
SPRINT II BURN-DOWN CHART DATA
Sprint | Day | Planned | Actual
2 |  | 17 | 14
| 1 | 11.33 | 8.5
| 2 | 5.66 | 5.5
Note on E6: Effort hours pending after day 1 of sprint 1
Note on E7: Effort hours pending after day 2 of sprint 1
Note on H7: Planned hours of effort in Sprint 1
Note on I7: Story points completed in sprint 1
Note on H8: Planned hours of effort in Sprint 2
Note on I8: Story points completed in Sprint 2
Note on E15: Effort hours pending after day 1 of sprint 2
Note on E16: Effort hours pending after day 2 of sprint 2

## Stand up Meeting
Sprint | US ID | Day | Assigned To | Points Discussed | Impediments | Action Taken
1 | US 02 | 1 | 1084752 | Validating whether the registered contact no is already presented in the database. | Struggle on validating the contact no. | Modified the Web-server to fetch the contact no and match with the existing contact number.
1 | US 03 | 2 | 1084752 | Search Available Package and Creation of card. | Struggle on implementing Packages.js file and search available packaged based on location .Struggle on creation on Card | Modified the Web-server to fetch the data for that given location and Modified the package.js component. Use Prime-react to create the card with desired format
2 | US 04 | 3 | 1084752 | Fetching the data for the searched package. | Struggle on creating the sidebar . | Learn More about prime-react to create the sidebar .
2 | US 06 | 4 | 1084752 | Fetching the planned booking data for that logged in user. | Struggle on fetching data for the logged in user. | Modified the web-server to update the database.

## Product Backlog Grooming
Sprint | US ID | Points Discussed
1 | US-03 | Search package which are searched by the user
2 | US-04 | Creation of Sidebar for package details and booking.
2 | US-05 | Check-out.